## Status Report
Stage | Address | Builder | Community | Schedule Date | Ready | Not Ready | Reason | % Ready
Trim | 2522 Thayne Drive | Windsor | Anna Crossing | 2016-11-28
Trim | 1514 Jamison Drive | Grand | Cumberland Crossing | 2016-11-28
Rough | 2413 Shenfield Drive | Beazer | Live Oak | 2016-11-30
Trim | 2213 Nuehoff Drive | Windsor | Anna Crossing | 2016-11-30
Status Report 11:00 Am
Patrick
11-28-16

## Daily on going Jobs
Stages | Address | Builder | Community | Crew | Schedule Date | Status | Time | Crew on Site | Hard Hats | Trash | Issues/Discuss with Crew | Crew ready for another house
Rough | 2428 Wrexham Dr | Beazer | Live Oak | Violeta | 2016-11-29
Daily on going Jobs 3:00 Pm

## Daily Walks
Stage | Address | Builder | Community | Crew | Stage Sent out | First Walk | 2nd Walk | Status of Walk | Issues/Punch | % Complete
TO | 4600 EVENSTAR WAY | LENNAR | HUDSON HEIGHTS | OLVERA/ ABRAHAM/ GERARDO/ GUILLERMO | 2016-11-23 | 2016-11-29
TO-V | 2401 SHENFIELD DRIVE | BEAZER | LIVE OAK | CARLOS PONCIO/ JAIME | 2016-11-28 | 2016-11-29
TRIM-V | 1313 GRAPEVINE COVE | BEAZER | TIRNITY FALLS | WINS SANCHEZ | 2016-11-18 | 2016-11-21 | 2016-11-29
TRIM-V | 1812 KESWICK DRIVE | BEAZER | LIVE OAK | RUBEN RAMIREZ | 2016-11-18 | 2016-11-21 | 2016-11-29
TRIM-V | 1608 BOYLE PARKWAY | GRAND | CUMBERLAND CROSSING | OLVERA/ VICTOR | 2016-11-18 | 2016-11-21 | 2016-11-29
TRIM-V | 4208 TALLULAH DRIVE | CB JENI | LOS RIOS | OLVERA/ VICTOR | 2016-11-18 | 2016-11-21 | 2016-11-29
TRIM-V | 4212 TALLULAH DRIVE | CB JENI | LOS RIOS | OLVERA/ VICTOR | 2016-11-18 | 2016-11-21 | 2016-11-29
TRIM-V | 4209 TALLULAH DRIVE | CB JENI | LOS RIOS | OLVERA/ VICTOR | 2016-11-18 | 2016-11-21 | 2016-11-29
TRIM-V | 7504 GUADALUPE WAY | BEAZER | TRINITY FALLS | WINS SANCHEZ | 2016-11-28 | 2016-11-29
TRIM-V | 4204 TALLULAH DRIVE | CB JENI | LOS RIOS | OLVERA/ VICTOR | 2016-11-28 | 2016-11-29
Daily Walks 5:00 Pm

## Incomplete
Stage | Address | Builder | Community | Crew | Stage Sent out | First Walk | 2nd Walk | Status of Walk | Issues/Punch | % Complete
Top Out | 726 Steppe Drive | Windsor | Murphy Meadows | Gallegos/ Diego/ JAIME | 2016-11-07 | 2016-11-10 | 2016-11-16 |  | punch not done
Top Out | 730 Steppe Drive | Windsor | Murphy Meadows | Gallegos/ Diego/ JAIME | 2016-11-07 | 2016-11-10 | 2016-11-16 |  | punch not done
TO | 722 Steppe Drive | Windsor | Murphy Meadows | Gallegos/ Diego/ JAIME | 2016-11-07 | 2016-11-11 | 2016-11-17 |  | punch not done
TO | 912 Aplatan Lane | Lennar | Hudson Heights | Olvera/Abraham/ JAIME | 2016-11-07 | 2016-11-16 | 2016-11-22 |  | Punch not complete
TRIM | 4608 EVENSTAR WAY | LENNAR | HUDSON HEIGHTS | OLVERA/ VICTOR | 2016-11-14 | 2016-11-16 | 2016-11-22 |  | Waiting on kitchen top
TRIM | 1538 HENNESSEY DRIVE | GRAND | CUMBERLAND CROSSING | OLVERA/ VICTOR | 2016-11-15 | 2016-11-16 | 2016-11-22 |  | Punch not done
TRIM | 4225 TALLULAH DRIVE | CB JENI | LOS RIOS | OLVERA/ VICTOR | 2016-11-15 | 2016-11-16 | 2016-11-22 |  | Crew not return
TRIM | 801 CIDERMONT DRIVE | LENNAR | HUDSON HEIGHTS | OLVERA/ VICTOR | 2016-11-16 | 2016-11-17 | 2016-11-23 |  | Waiting on tile
TRIM | 1525 JAMISON DRIVE | GRAND | CUMBERLAND CROSSING | OLVERA/ ROGELIO | 2016-11-16 | 2016-11-17 | 2016-11-23 |  | Waiting on tub and tile in master
TRIM | 2405 SHENFIELD DRIVE | BEAZER | LIVE OAK | RUBEN RAMIREZ | 2016-11-17 | 2016-11-18 | 2016-11-28 |  | Crew not return
TRIM | 4221 TALLULAH DRIVE | CB JENI | LOS RIOS | OLVERA/ VICTOR | 2016-11-17 | 2016-11-18 | 2016-11-28 |  | punch not done
TRIM | 2409 SHENFIELD DRIVE | BEAZER | LIVE OAK | RUBEN RAMIREZ | 2016-11-17 | 2016-11-18 | 2016-11-28 |  | Crew not return
Incomplete 5:00 Pm

## Complete (hidden)
Stage | Address | Builder | Community | Crew | Stage Sent out | First Walk | 2nd Walk | Status of Walk
Trim | 2404 Wrexham Drive | Beazer | Live Oak |  | 2016-06-21 | 2016-06-22 | 2016-06-28 | Complete
Trim | 1312 Caney Creek Lane | Beazer | Trinity Falls |  | 2016-06-21 | 2016-06-22 | 2016-06-28 | Complete
Trim | 805 Cidermont Drive | Lennar | Hudson Heights | Joel Ezqueda | 2016-06-23 | 2016-06-24 | 2016-06-29 | Complete
Trim | 808 Feathering Way | Lennar | Hudson Heights | Joel Ezqueda | 2016-06-23 | 2016-06-24 | 2016-06-29 | Complete
Trim | 805 Feathering Way | Lennar | Hudson Heights | Joel Ezqueda | 2016-06-23 | 2016-06-24 | 2016-06-29 | Complete
Trim | 804 Feathering Way | Lennar | Hudson Heights | Joel Ezqueda | 2016-06-28 | 2016-06-29 | 2016-07-06
Trim | 4508 Evenstar Way | Lennar | Hudson Heights | Victor/Olvera | 2016-06-29 | 2016-06-30 | 2016-07-07 | Complete
Trim | 626 Warner Drive | Windsor | Anna Crossing | Beto/Olvera | 2016-06-29 | 2016-06-30 | 2016-07-07 | Complete
Top Out | 809 Aplatan Lane | Lennar | Hudson Heights | Carlos Aguillon/Olvera | 2016-06-28 | 2016-06-30 | 2016-07-07 | Complete
Top Out | 1317 Madrid Falls Drive | Beazer | Trinity Falls | Luis Reyes/ Jaime | 2016-07-19 | 2016-07-21 | 2016-07-27 | Complete
Top Out | 4209 Tallulah Drive | CB Jeni | Los Rios | Federico Gonzalez/ Olvera/ Orejon | 2016-07-25 | 2016-07-27 | 2016-08-02 | Complete
Top Out | 4213 Tallulah Drive | CB Jeni | Los Rios | Edgar/Olvera/ Olvera/ Orejon | 2016-07-25 | 2016-07-27 | 2016-08-02 | Complete
Top Out | 4205 Tallulah Drive | CB Jeni | Los Rios | Federico Gonzalez/ Olvera/ Orejon | 2016-07-25 | 2016-07-28 | 2016-08-03 | Complete
Top Out | 4217 Tallulah Drive | CB Jeni | Los Rios | Edgar/Olvera/ Olvera/ Orejon | 2016-07-25 | 2016-07-28 | 2016-08-03 | Complete
Top Out | 1518 Jamison Drive | Grand | Cumberland Crossing | Olbaldo/Dionisio / Jaime | 2016-07-28 | 2016-08-01 | 2016-08-05 | Complete
Trim | 7525 West Fork Lane | Beazer | Trinity Falls | Ruben Ramirez | 2016-07-29 | 2016-08-01 | 2016-08-05 | Complete
Trim | 2240 Caniesto Street | CB Jeni | Los Rios | Joel Esqueda | 2016-08-02 | 2016-08-03 | 2016-08-09 | Complete
Trim | 2236 Caniesto Street | CB Jeni | Los Rios | Joel Esqueda | 2016-08-02 | 2016-08-03 | 2016-08-09 | Complete
Top Out | 2505 Thayne Drive | Windsor | Anna Crossing | Edgar/Olvera/ Jesus Gonzalez | 2016-08-01 | 2016-08-03 | 2016-08-09 | Complete
Trim-V | 7408 Sabine Drive | Beazer | Trinity Falls | Wins Sanchez | 2016-08-04 | 2016-08-05 | 2016-08-11 | Complete
June - Complete

## Plans
Stage | Address | Builder | Community | Due date | Ready | Not Ready | Issues/Confirmation
Rough | 7528 Guadalupe Way | Beazer | Trinity Falls | 2016-11-29
Rough | 2012 evelyn | Windsor | Anna Crossing | 2016-11-30
Rough | 7205 East Fork | Beazer | Trinity Falls | 2016-12-02
New Plan request

## Sheet1 (hidden)
Stages | Rough | TopOut | Trim
Rough | Violeta | Dionisio Paz | Ruben Ramirez
Top Out | Victor H | Miguel Briseno | Joel Ezqueda
Trim | Manolo | Baltazar Mejia | Wins Sanchez
| Alvaro | Juan Mejia | Victor/Olvera
|  | Juan Soto | Jorge/Olvera
|  | Carlos Poncio | Rogelio/Olvera
|  | Maximino Orta | Beto/Olvera
Luis Reyes
Fede/ Luis Reyes
Salvador/ Luis Reyes
Guillermo Gallegos
Jaime Gallegos
Diego Gallegos
Martin Olalde
Jose Olvera
Armando/Olvera
Carlos Aguillon/Olvera
Jose Vizcaya/Olvera
Edgar/Olvera
Abraham/Olvera
Oscar Luna
Builder | Lennar | Beazer | Grand | Windsor | Chesmar | Castle Rock | Darling | MI | CbJeni
Lennar | Artesia | Arrow Brooke | Bower Ranch | Alanis Crossing | Buffalo Creek | Inspiration | Tucker Hill |  | Brick Row
Beazer | Bear Creek | Canyon Falls | Cumberland Crossing | Anna Crossing | Savannah | Savannah |  |  | Cottonwood
Grand | Brentwood | Craig Ranch | Las Brisas | Braddock Place | The Preserves | Viridian |  |  | Cypress Meadow
Windsor | Chamberlain Crossing | Creeks of Legacy | Panther Creek | Breezy Hill | Windsong Ranch |  |  |  | Grand Park Canal
Chesmar | Creeks of Legacy | Erwin Farms | Shiloh Ranch | Carillon |  |  |  |  | Hometown
Castle Rock | Cross Oaks | Frisco Hills | Sorrellwood | Colby Crossing |  |  |  |  | Los Rios
Darling | Crown Ridge | Live Oaks | The Ridge | Coventry Crossing |  |  |  |  | McKinney Ranch
MI | Forest Meadow | Miramonte | Estates of Verona | Cumberland Crossing |  |  |  |  | Mustang Park
CB Jeni | Heartland | Paloma Creek |  | Stone Creek |  |  |  |  | Raiford Crossing
| Hidden Cove | Pecan Creek | [6 empty] | Stacy Crossing
| Hudson Heights | Prestwyck | [6 empty] | Twin Creeks
| Legends | Rolling Meadow | [6 empty] | Viridian
| Mistletoe Hills | Stoney Creek
| Parkside West | Sunset Pointe
| Pecan Ridge | Trinity Falls
| Prestwyck | Wildwood
| Primrose Crossing | Williamsburg
| Richfield | Willow Ridge
Sendera Ranch
Somerset
Sonoma Verde
Villages of Stone Lake
Trophy Club
Waters Edge
Wyndale Meadows