## WEEK 111725
DAILY SCHEDULE
Week of: | 2025-11-17
| 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23
| MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
Everado: | 2025-11-17: 790 COUNTY ROAD 2480 HICO TX (GATE CODE:1982) STAINED CONCRETE; 2025-11-19: Rescheduled 6165 Tyrone Dr, Dallas-in city limits
806 West Main st, honey grove (in city limits)
Lamberto:
Thomas: | thomas off | 803 FM 1637 VALLEY MILLS TX (GATE CODE:2429#) DAD IS MASTER PLUMBER-trim | 8421 CR 308 GRANDVIEW TX-INSTALL KITCHEN FIXTURE NOW THAT COUNTERTOP HAS BEEN INSTALLED, INSTALL PRV AND EXPANSION TANK(already invoiced) also installl fireplace key and escucheon. | 1752 FM 489 OAKWOOD-trim | 803 FM 1637 valley mills finish tub and add. Prv and expansion tank (everything is already delivered to jobsite
|  |  | Tilson Warranty 1561 County Road 215 Bertram Call or Text Mitchell (512)944-5732 when on your way Master shower faucet handle is pulling away from the wall | 163 Canal St Corsicana - Trim Tub in our shop
104 West Senterfeit St Lometa STAINED CONCRETE "IN CITY LIMITS"-Master Bathroom toilet is not flushing well, probably needs snaked -Master Bathroom left hand vanity sink stopper not holding water -Bath 2 sink stopper not holding water -Bath 3 faucet head is loose
2491 CR 3270 KEMPNER TX (GATE CODE:2025)-Master Bathroom vanity faucets are loose -Water heater drain lines are too short -Please leave another water shut off box so I can add it once grading is brought up
Juan: | bar: 2025-11-23
Terry : | 2025-11-17: 610 S 28th St corsicana - Rough; 2025-11-18: 790 COUNTY ROAD 2480 HICO TX (GATE CODE:1982) STAINED CONCRETE-ROUGH; 2025-11-20: Rescheduled 6165 Tyrone Dr, Dallas-rough in city limits
Jorge | 2025-11-20: 4005 Rolling Wood, midltohain-topout
Cory: | 2025-11-17: 833 CLEAR COVE COURT N, GRAFORD (GATE CODE;71090)- TOPOUT NO GAS Waterline at utility is out of wall, Master toilet vent sightly out of wall,master shower vent pipe slightly out of wall (exterior side); 2025-11-18: 806 West Main st, honey grove-rough (in city limits); 2025-11-21: 409 BLUE CUT RD SOUTH MOODY TX -topout NO GAS

## WEEK 112425
DAILY SCHEDULE
Week of: | 2025-11-24
| 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30
| MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
Everado: | 2025-11-25: 6165 Tyrone Dr, Dallas-in city limits; 2025-11-27: HOLIDAY; 2025-11-28: HOLIDAY
|  |  |  | HOLIDAY | HOLIDAY
|  |  |  | HOLIDAY | HOLIDAY
Lamberto: | 2025-11-27: HOLIDAY; 2025-11-28: HOLIDAY
|  |  |  | HOLIDAY | HOLIDAY
Thomas: | 2025-11-24: 2751 E STATE HWY 34 ENNIS-Trim; 2025-11-25: 701 Knox, Ennis-trim; 2025-11-27: HOLIDAY; 2025-11-28: HOLIDAY
| Thomas finish 163 canal st Corsicana |  |  | HOLIDAY | HOLIDAY
Juan: | 2025-11-24: 4005 Rolling Wood, midltohain- 3 hvac, 2 tankless, dryer, fireplace, incoming; 2025-11-27: HOLIDAY; 2025-11-28: HOLIDAY
|  |  |  | HOLIDAY | HOLIDAY
Terry : | 2025-11-26: 6165 Tyrone Dr, Dallas-rough in city limits; 2025-11-27: HOLIDAY; 2025-11-28: HOLIDAY
|  |  |  | HOLIDAY | HOLIDAY
Jorge: | 2025-11-27: HOLIDAY; 2025-11-28: HOLIDAY
|  |  |  | HOLIDAY | HOLIDAY
Cory: | 2025-11-24: 6440 Mulberry, Midlothian-topout; 2025-11-25: 150 WOODLAKE LANE AXTELL TX (1-1/4 waterline)-topout; 2025-11-26: 431 BROWN COUTNTY ROAD 175 BANGS TX (GATE CODE :3825) STAINED CONCRETE; 2025-11-27: HOLIDAY

## WEEK 12125
DAILY SCHEDULE
Week of: | 2025-12-01
| 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07
| MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
Everado: | bar: 2025-12-07
Lamberto:
Thomas: | 2025-12-01: 13685 REEDS LAKE LOOP ROGERS TX-TRIM
Juan: | bar: 2025-12-07
Terry :
Jorge:
Cory: | 2025-12-01: 13 SPORTSMAN DRIVE MINERAL WELLS TX (1 1/4 waterline)-topout; 2025-12-03: 472 ROYAL SANTANA RUN WEATHERFORD TX Waterline is 1 1/4 -topout; 2025-12-04: 714 W Avenue I, midlothian topout Plumbing; 2025-12-05: 1797 A FM 202 GLEN ROSE TX -topout (already asked corey and he wants this day

## WEEK 12825
DAILY SCHEDULE
Week of: | 2025-12-08
| 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14
| MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
Everado: | bar: 2025-12-14
Lamberto:
Thomas: | 2025-12-09: 400 GABRIEL FOREST RD GEORGETOWN TX-TRIM
Juan: | bar: 2025-12-14
Terry :
Jorge:
Cory: